## Sheet1
				Remaining Effort (hrs) / Sprint Timeline

		ss

Day0	Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8
55	23	32	62	11	0	0	0	0

55	23	32	62	11	0	0	0	0

## Sheet2
Story #	Feature	Sprint Backlog Item	Task #	Volunteer	Task Details	Initial Effort Estimate (hrs)	New Estimates of Effort remaining at end of					Status
				Day1	Day2	Day3	Day4	Day5	Day6	Day7	Day8
US001	Register and login Customer	As a Customer I am able to register and login to the website	Task 1	Mukhesh Sure	Code Review	4	2	2					Completed
			Task 2	Dhanraj Shinde	Frontend	3	1	2					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US002	Register and Login Admin/Employee	As a Admin/Employee, I am able to register Employees(Admin) and login to the website	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	Frontend	3	1	1	1					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2		1		1					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US003	Customer Check Balance	The entered data is validated according to the constraints.	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	Frontend	3	1	1	1					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2		1		1					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US004	Customer Deposit & Withdrawl	As a Customer,I am able to deposit & withdraw money	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	Frontend	3	1	1	1					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				1					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US005	Employee (Create & Delete)	As a Employee, I am able to add and delete Customers	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	Frontend	3	1	1	1					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				1					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US006	Employee (Read & Update)	As a Employee, I am able to read(view) and update Customers	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	Frontend	3	1	1	1					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US007	Admin (Create & Delete)	As an Admin, I am able to add and delete Employees	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	Frontend	3	1	1	1					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US008	Admin (Read & Update)	As an Admin, I am able to read(view) and update Employees	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	Frontend	3	1	1	1					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US009	Employee Logout	As an Employee, I am able to log out and go to the landing page.	Task 1	Mukhesh Sure	Code Review	7	2	1		1		2	1		Completed
			Task 2	Dhanraj Shinde	Frontend	3	1					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US010	Coustomer Logout	As an Customer, I am able to log out and go to the landing page.	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	Frontend	3	1	1	1					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US011	Random Genrator	Employee Id's and Customer Id's should be managed & auto-genrated(auto-incremenented) by the system	Task 1	Mukhesh Sure	Code Review	4	2	1		1					Completed
			Task 2	Dhanraj Shinde	Frontend	3	1	1	1					Completed
			Task 3	Shivam Mishra	Backend	2	2					Completed
			Task 4	Jatin Rastogi	Testing	2			1	1					Completed
			Task 5	Ashwini Yadav	Defect fixing	2				2					Completed
			Task 6	Ruchitha s	Execute the tests	3			1	2					Completed
				Completed
US012	Validation Util	The entered data is validated according to the constraints.	Task 1	Mukhesh Sure	Code Review
			Task 2	Dhanraj Shinde	Frontend
			Task 3	Shivam Mishra	Backend
			Task 4	Jatin Rastogi	Testing
			Task 5	Ashwini Yadav	Defect fixing
			Task 6	Ruchitha s	Execute the tests

				Total	183	55	25	31	61	0	2	1